## Sheet1
| NAME: | KAYODE PETER TEMITOPE
| MATRIC NO: | 208077 (300 Level)
| COURSE: | CSC 302 Assignment
CHAPTER 3: QUESTION 8, GANTT CHART
Activity No | Activity | Time (Weeks) | Immediate Predecessors | Gantt Chart
|  |  |  | Wk 1 | wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14 | Wk 15 | Wk 16 | Wk 17 | Wk 18 | Wk 19 | Wk 20 | Wk 21 | Wk 22
1 | Collect Requirement | 3
2 | Analyze Process | 2 | 1
3 | Analyze Data | 2 | 2
4 | Design Processes | 6 | 2
5 | Design Data | 3 | 3
6 | Design Screens | 2 | 3, 4
7 | Design Report | 4 | 4, 5
8 | Program | 5 | 6, 7
9 | Test and Document | 7 | 7
10 | Install | 2 | 8, 9

## Sheet2
| NAME: | KAYODE PETER TEMITOPE
| MATRIC NO: | 208077 (300 Level)
| COURSE: | CSC 302 Assignment
CHAPTER 3: QUESTION 9
Activity No | Activity | Time (Weeks) | Immediate Predecessors | Earliest Expected Completion Time
1 | Collect Requirement | 6 |  | 6
2 | Analyze Process | 4 | 1 | 10
3 | Analyze Data | 4 | 2 | 14
4 | Design Processes | 18 | 2 | 28
5 | Design Data | 6 | 3 | 20
6 | Design Screens | 4 | 3, 4 | 32
7 | Design Report | 12 | 4, 5 | 40
8 | Program | 10 | 6, 7 | 50
9 | Test and Document | 14 | 7 | 54
10 | Install | 4 | 8, 9 | 58 | Network Diagram
11 | New Activity | 1 | 9,10 | 59
1
2
3
4
5
6
7
9
8
10
11